## Intro
Project Name: Life Reconstruction & Pivot (Project LRP)
Project Manager: Venkatesh.R
Project Sponsor: Personal Well-being & Future CareerSection
Description : Project PurposeTo stabilize mental health, fulfill caregiving duties, and gain [Skill] to re-enter the workforce.

## Prj Charter
Section | Description
Project Purpose | To stabilize mental health, fulfill caregiving duties, and gain [Skill] to re-enter the workforce.
High-Level Goals | 1. Achieve a baseline of mental stability. 2. Provide consistent care. 3. Complete [Skill] Certification.
Success Criteria | Consistent 2-week Sprints completed; Health metrics (sleep/mood) improved; Portfolio/Cert finished.
Fixed Constraints | Fixed caregiving hours; limited financial runway.
Flexible Constraints | Pace of upskilling; specific daily schedule (based on energy).

## WBS
No | Task | Owner | Start Date | End Date | Comments
1 | 1.0 Health & Recovery (Priority 0)
1.1 Clinical: Therapy sessions, medication management.
1.2 Holistic: Sleep hygiene, nutrition, 15-min movement.
2 | 2.0 Caregiving (Operational)
2.1 Daily Essentials: Meals, hygiene assistance, medication.
2.2 Administrative: Doctor appointments, insurance/billing.
3 | 3.0 Upskilling (Growth)
3.1 Learning: Theory, coursework, or tutorials.
3.2 Application: Building a portfolio or practice projects.
4 | 4.0 Career Pivot (Output)
4.1 Resume/LinkedIn updates; Networking; Interview prep.

## Risk-reg
Risk ID | Risk Description | Impact | Mitigation Strategy (Pre-event) | Contingency Plan (Post-event)
R1 | Depressive Episode (Low Energy) | High | Schedule "Minimum Viable Days" in advance. | Trigger "Low Capacity" Sprint mode (Caregiving only).
R2 | Caregiver Burnout | Medium | Scheduled 1-hour "Deep Silence" or break daily. | Request external help/respite for 24 hours.
R3 | Upskilling "Plateau" | Low | Break lessons into 10-minute micro-tasks. | Switch to passive learning (podcasts/videos).

## Stakeholder Details
Stakeholder | Role | Expectations | Influence | Strategy
Yourself | Project Manager | Recovery & Success | High | Practice self-compassion; avoid "over-planning."
Care Recipient | Primary Beneficiary | Safety & Care | High | Maintain clear routine to reduce anxiety.
Medical Team | Subject Matter Experts | Clinical Progress | Medium | Provide data/symptoms clearly.
Professional Network | Potential Sponsors | Industry Insights | Low/Med | Passive networking (LinkedIn) until Sprint 3+.

## RiskRegistry
Issue ID | Description | Severity | Action Taken | Status
I-01 | Insomnia spike (3 days) | High | Reduced upskilling hours; prioritized naps. | Resolved
I-02 | Tech difficulty in course | Low | Emailed support; moved to a different module. | Open
I-03 | Caregiving burnout | Medium | Outsourced meal prep for 2 days. | Monitoring

## Stakeholder
Stakeholder | Method | Frequency | Objective
Doctor/Therapist | In-person/Telehealth | Bi-weekly | Report health metrics & adjust treatment.
Family/Support | Text/Chat | Daily | Update on energy levels (Red/Yellow/Green status).
Care Recipient | Verbal | Continuous | Manage expectations for the day’s activities.
Mentors/Peers | LinkedIn/Email | Weekly | Stay connected to the industry.

## Agile
Instead of a rigid 6-month plan, work in 2-week chunks.
Sprint Planning: Every Sunday. Assess energy. If energy is low, plan a "Maintenance Sprint" (60% capacity). If high, plan a "Growth Sprint" (100% capacity).
Daily Standup (Internal): Every morning, ask:
What did I do yesterday for my recovery?
What is my one priority today?
What is blocking my mood or progress?
Sprint Retrospective:
Every second Saturday. Ask: "What was too heavy this week? What made me feel capable?" Adjust the next Sprint accordingly.

## CR
Change Request Form (Agile Pivot)
In PMP, changes are formal. In my project, i use when i need to change your Upskilling path or Recovery plan.
Proposed Change: (e.g., Switching from Learning Python to Management).
Reason: (e.g., Management aligns better with current cognitive energy levels).
Impact on Schedule: Adds 3 weeks to the timeline.
Decision: Approved (Self-authorization based on mental health assessment).

## Project Closing
Handover: Transition caregiving duties (if applicable) or integrate them into a work schedule.
Final Product: Updated Resume + [Skill] Certification + 3 Portfolio pieces.
Lessons Learned: Document the triggers discovered during the project to prevent future burnout.
Sign off.

## Closing Documents
The "Closing" Document (Transition to Employment)
When the project ends, you don't just "start a job"—you transition.
Project Archive: Save your course certificates and "Lessons Learned" (e.g., "I work best between 10 AM and 2 PM").
Benefits Realization: Did the project improve your health baseline?
Formal Closure: Acknowledge the end of the "Job Loss" phase and the start of the "Career 2.0" phase.